🏗️

CONSTRUCTION PMO

PERFORMANCE ANALYTICS

Insight Report

Prepared by:

MONSURU ADELEKE

Data Analyst  |   Civil Engineering Graduate

Nigeria  |  2026

Tools Used:

SQL Server (SSMS)  |  Microsoft Excel  |  GitHub

1. Executive Summary

This report presents the findings of a structured data analysis conducted on 50 infrastructure construction projects across 10 Nigerian states. Using SQL Server for data modelling and validation, and Microsoft Excel for visualization, the analysis identifies the root causes of cost overruns, schedule delays, and contractor under performance and delivers actionable recommendations for the Project Management Office (PMO).

Key Findings at a Glance:

- 47 out of 50 projects (94%) exceeded their approved budgets, with a combined net cost overrun of ₦15.1 billion across the portfolio.

- The Procurement phase is the single largest risk area, averaging a 24.1% cost overrun, higher than any other project phase.

- PRJ-005 (Kano Erosion Control Phase 2) recorded the highest individual cost overrun at ₦842.8 million - 54.1% above its approved budget.

- Horizon Builders is the lowest performing contractor with a performance score of 25.7% across 10 projects, driven by a 31.4% average cost overrun and 42.9% average duration overrun.

- Grandeur Works is the highest  performing contractor with a score of 53.0%, demonstrating that better contractor selection can materially reduce project risk.

| Total Projects | Total Cost Overrun | Avg Schedule Delay | High Risk Projects |
| --- | --- | --- | --- |
| 50 | ₦15.1 Billion | 10.4 Months | See Q4 Analysis |

2. Methodology

2.1 Data Source

The dataset was purposely built to simulate a realistic Nigerian construction PMO environment. It comprises three related tables:

- Projects : 50 project records across 10 Nigerian states, 10 project types, and 10 contractors

- Phase Breakdown : 300 records capturing budget and actual spend across 6 project phases per project

- Contractor Scorecard : 10 aggregated contractor performance records

2.2 Tools & Process

- SQL Server (SSMS) : Used for database design, data validation, and analytical querying

- Microsoft Excel : Used for visual inspection, pivot table analysis, and dashboard creation

- GitHub : Used for version control and project documentation

The analysis followed a structured five phase workflow:

- Phase 1: Dataset design and generation

- Phase 2: Database creation, data import, and validation

- Phase 3: SQL-based analysis answering five business questions

- Phase 4: Excel dashboard with interactive slicers and charts

- Phase 5: Insight report with recommendations (this document)

3. Key Findings

3.1 Cost & Schedule Overruns — Which projects are the biggest problem?

The analysis revealed that cost overruns are widespread across the portfolio. 47 of 50 active projects (94%) exceeded their approved budgets, with only 3 projects coming in under budget. The total net cost overrun across the portfolio stands at ₦15.1 billion.

Highest Cost Overrun — PRJ-005:

| Project ID | Project Name | Budget (₦) | Overrun (₦) | Overrun % | Status |
| --- | --- | --- | --- | --- | --- |
| PRJ-005 | Kano Erosion Control Phase 2 | ₦1.56B | ₦842.8M | 54.1% | Ongoing |

PRJ-005 represents a critical intervention point. At 54.1% above its approved budget with 16 months of schedule delay, this project alone accounts for a significant proportion of portfolio-level financial risk. Its ongoing status means losses are still accumulating.

3.2 Phase Risk — Where in the project life cycle does money get lost?

Breaking down cost overruns by project phase reveals that the Procurement phase is consistently the most financially risky phase across all 50 projects.

| Phase | Projects | Total Overrun (₦) | Avg Overrun % |
| --- | --- | --- | --- |
| Procurement | 50 | ₦1.39 Billion | 24.1% — Highest Risk Phase |

The Procurement phase, covering material sourcing, vendor selection, and contract awards recorded an average cost overrun of 24.1%, the highest of any phase. This suggests systemic weaknesses in vendor management, price escalation controls, and procurement planning. The Construction phase, while largest in absolute cost, had a lower relative overrun rate, suggesting execution is better controlled than procurement.

3.3 Contractor Performance — Does contractor selection predict outcomes?

Contractor performance varies significantly across the portfolio. The gap between the best and worst performing contractor is 27.3 percentage points, a difference large enough to materially determine whether a project succeeds or fails.

| Contractor | Projects | Avg Cost Overrun | Avg Duration Overrun | Score | Rating |
| --- | --- | --- | --- | --- | --- |
| Grandeur Works | 6 | 18.8% | 28.2% | 53.0% | Average |
| Horizon Builders | 10 | 31.4% | 42.9% | 25.7% | Poor |

Horizon Builders handled the most projects (10) yet recorded the worst performance score (25.7%). This combination of high project volume and poor performance  indicates that award decisions may not have been sufficiently informed by past performance data. Grandeur Works, with fewer projects and lower overrun rates, demonstrates that better managed contractors deliver measurably better outcomes.

3.4 Early Warning Signs — Which active projects are heading for trouble?

Using a composite risk score derived from cost overrun percentage and schedule delay percentage, active projects were classified into three risk tiers:

| Risk Category | Classification Criteria | Implication |
| --- | --- | --- |
| High Risk | Risk score ≥ 50 OR Formally Delayed | Immediate intervention required |
| Moderate Risk | Risk score 20–49, completion > 50% | Close monitoring needed |
| Low Risk | Risk score < 20, completion > 50% | On track — maintain current approach |

The interactive dashboard allows stakeholders to filter risk flags by state and project status to identify geographic concentrations of at-risk projects.

3.5 Improvement Areas — Where should the PMO focus its efforts?

Analyzing High Risk projects across four dimensions  delay reason, state, project type, and supervising consultant  identifies the most frequent structural causes of failure:

- Delay Reason: The most frequent causes of high-risk outcomes are funding delays, contractor defaults, and poor site supervision  all of which are addressable through better contract management and payment scheduling.

- State: Certain states show higher concentrations of high risk projects, suggesting regional factors such as logistics, regulatory friction, or community engagement challenges.

- Project Type: Some project categories  such as drainage systems and erosion control show higher average risk scores, indicating that technical complexity is not always matched by adequate risk provisions.

- Consultant: Performance variation across supervising consultants mirrors the contractor performance findings  consultant selection has a measurable impact on project outcomes.

4. Recommendations

Based on the findings above, the following five recommendations are presented for the PMO's consideration:

- Reform the Procurement Process

The Procurement phase consistently produces the highest overruns (24.1% average). The PMO should implement structured vendor pre-qualification, introduce price escalation clauses tied to commodity indices, and require independent cost verification before procurement approvals.

- Introduce a Contractor Performance Registry

Horizon Builders' poor performance (25.7% score across 10 projects) was not reflected in its award volume. The PMO should maintain a formal performance registry that ties future contract awards to historical performance scores. Contractors scoring below 35% should be placed on probation and excluded from new awards until performance improves.

- Deploy an Early Warning Monitoring System

The risk scoring framework developed in this analysis, combining cost overrun percentage and schedule delay percentage  should be implemented as a monthly monitoring tool. Projects crossing the High Risk threshold should trigger an automatic management review within 30 days.

- Address Funding Delay as a Structural Problem

Funding delay emerged as one of the most frequent causes of high risk outcomes. The PMO should work with the finance function to establish dedicated project reserve funds and streamline payment approval workflows. Contractor default, often caused by delayed payments  can be significantly reduced through more reliable cash flow management.

- Prioritize Immediate Intervention on PRJ-005

The Kano Erosion Control Phase 2 project (PRJ-005) represents the single largest financial risk in the portfolio at ₦842.8 million overrun (54.1% above budget) with 16 months of delay. An immediate project audit should be commissioned, with a revised cost-to-complete estimate and a clear recovery plan submitted to leadership within 60 days.

5. Limitations

The following limitations should be considered when interpreting the findings of this analysis:

- Simulated Dataset: The dataset was purpose built to simulate realistic conditions. While the data reflects real world patterns, findings should be validated against actual project records before informing formal policy decisions.

- No Time Series Dimension: The analysis captures a snapshot of project performance. It does not model how performance evolves over time within individual projects, which would require longitudinal data.

- Single Primary Delay Reason: Each project was assigned one primary delay reason. In practice, projects typically suffer from multiple overlapping causes, which this dataset does not fully capture.

- No External Factors: Macroeconomic variables such as inflation rate, foreign exchange fluctuations, and fuel price movements  all of which significantly affect construction costs in Nigeria  were not modeled in this dataset.

- Contractor Score Methodology: The performance score is a composite of cost and duration overrun metrics only. It does not account for quality of workmanship, safety record, or stakeholder satisfaction all relevant dimensions of contractor performance.

6. Conclusion & Next Steps

This analysis demonstrates that cost overruns and schedule delays in the Nigerian construction sector are not random events, they follow identifiable patterns that can be detected, measured, and addressed through structured data analysis.

The PMO has a clear opportunity to reduce financial losses by targeting three high leverage areas: 1. reforming procurement controls

- implementing performance based contractor selection

- deploying an early warning monitoring system.

Next Steps:

- Validate findings against real project data from active portfolios

- Implement the risk scoring model as a live monthly dashboard

- Commission an immediate audit of PRJ-005

- Present findings to PMO leadership and procurement committee

- Expand the dataset to include quality, safety, and stakeholder metrics

Report prepared as part of the Construction PMO Analytics Portfolio Project

GitHub: https://github.com/Shile-tech/Construction_PMO_Analytics  |  LinkedIn: www.linkedin.com/in/adeleke-monsuru